STRATEGIC NOTE — Ubuntu Academy 3.0

Vision, positioning, and development trajectory

## 1. Starting Point

Ubuntu 3.0 represents a structuring step for the Ubuntu Academy project. At this stage, integrating a full e-learning module would entail:

heavier technical development,

continuous production of structured content,

greater complexity for users,

technical requirements that are sometimes far removed from on-the-ground realities.

Yet the priority needs identified to date are clear:

better track learning pathways,

structure monitoring and evaluation,

strengthen the professional posture of assistant trainers,

and improve the clarity and rigor of reports.

The proposed strategy therefore focuses the Ubuntu 3.0 project on these fundamentals. The aim is not to abandon e-learning, but to follow a logical order of construction.

## 2. Strategic Positioning

Launch Ubuntu 3.0 as a platform for managing learning pathways and monitoring & evaluation (M&E), without an integrated e-learning module in the first version. This choice rests on three principles:

a) Priority to real-world use: First consolidate what is already being practiced in the field.

b) Progressive mastery of complexity: Stabilize data flows before adding digital pedagogical layers.

c) Technical solidity: Build a clear and scalable architecture, capable of later integrating an e-learning module if relevant.

The integration of an e-learning module may be considered later, when:

uses are stabilized,

data are reliable,

teams are fully comfortable with the tool,

and technical conditions allow it.

## 3. Guiding Design Principles

### a. Mastered simplicity

Simplicity does not mean minimalism, but clarity. Ubuntu 3.0 must:

run on simple Android devices,

tolerate limited connectivity,

offer a clear and structured interface,

allow quick and intuitive actions.

The goal is for teams to be able to use it easily on a daily basis.

### b. Immediate operational usefulness

The platform must address concrete needs:

centralize data that is currently scattered,

simplify and shorten the reporting process,

provide a comprehensive view of cohorts and groups,

facilitate the monitoring of sessions and learning pathways.

Each feature must be tied to an identifiable operational gain.

### c. Rigor of monitoring and evaluation

Ubuntu 3.0 must enable:

the structured collection of quantitative data (participation, sessions, progression),

the integration of qualitative data (stories, visual or audio elements depending on context),

the ability to extract consolidated and usable data.

The challenge is not merely to collect data, but to produce information that supports decision-making.

## 4. Built-in Governance and Ethics

The platform must integrate from the outset:

explicit role management (learner, assistant, trainer, administrator),

a consent system for the use of stories and media materials,

traceability of validations.

These elements contribute directly to the reliability and continuity of the project.

## 5. Strengthening Local Capacities

Ubuntu 3.0 must help structure the professional development of assistant trainers:

monitoring of professional posture,

regular updating of follow-up reports,

supervised and traceable validation and certification,

continuous co-construction with the IT/AI team and field teams.

The platform must support autonomy and professionalization.

## 6. Functional Scope

### a. Pathway management

Creation and management of cohorts and groups

Participant registration

Session tracking (date, theme, attendance)

Follow-up notes and simple alerts

### b. Self-assessment

Simple, multilingual questionnaires

Progress visualization

Individual and collective summaries

### c. Integrated monitoring and evaluation

Consolidated quantitative indicators

Data extracts ready for reports

Structured storytelling (text, audio, photo depending on field capacity)

### d. Assistant-trainer pathway

Professional posture monitoring

Formalized ethical commitments

Follow-up reports

Validation and certification system with traceability

### e. AI

Rephrasing assistance

Translation

Writing support

## 7. Step-by-Step Development Approach

Step 1: Stabilization

Objective: put in place a reliable foundation for management and M&E.

Main deliverables:

cohort and group management,

session tracking,

key monitoring indicators,

structured storytelling,

export files consolidating key data.

Step 2: Professional Structuring

Objective: strengthen posture and steering capacity.

Deliverables:

dashboards,

assistant-trainer monitoring,

reports consolidating all key data,

certification.

Step 3: Controlled Extension

Objective: extend functionality gradually, based on real needs.

Possibilities:

skills portfolio,

employability tracking,

automatically generated reports,

possible integration of an e-learning module if conditions are met.

## 8. Expected Impacts

Improved pedagogical quality through more coherent monitoring

Better steering capacity thanks to consolidated data

Strengthened professionalization of assistant trainers

Clearer and more reliable reports for partners and donors.

## 9. Conclusion

Ubuntu 3.0 must be designed as an infrastructure for steering and transmission.

The priority is to:

a) Structure pathways and organize data.

b) Consolidate monitoring and professional posture.

c) Then extend gradually toward other features if relevant.

This step-by-step approach makes it possible to move forward in a coherent, solid, and sustainable way.